## Sheet1
User Story | Tasks | Assigned to | Estimated time | Actual time | Done? | Notes | Additional information
The user must be able to register and login | Wrapper Classes | Filip | 16h | 14h
| Models | Filip
| Endpoints | Filip
| Testing | Filip
The user must be able to create HOAs | Wrapper Classes | Dimitar | 1h 30 mins | 2h
| Authentication Classes | Dimitar | 4h 30 mins | 3h 30 mins
| H2 Configuration | Dimitar | 1h 30 mins | 2h
| Structure Establishment | Dimitar | 15 mins | 30 mins
| Testing | Dimitar | 5 hours | 6 hours
| Repository Creation | Dimitar & Atour | 3 hours | 3 hours
| Endpoint Creation | Atour | 30 mins | 1 hour
The users can receive notifications of accepted proposals | Structure Establishment | George | 4 hours | 4h 30 mins |  |  | Even though it is not in our biggest priorities, I started working on it as it wasn't dependent on anything else. The rest of the issues were dependent on the assigned ones in this sprint.
| Notifications service | George
| Endpoint with request validation | George
| Email sending with SendGrid | George
| Integrate the notifications in other microservices | [5 empty] | The proposals are not implemented yet and the task will be done in future sprint
User Story | Tasks | Assigned to | Estimated time | Actual time | Done? | Notes | Additional information
Unit testing the HoaUser | Test wrapper classes | Filip | 3h | 3h
| Test HoaUser | Filip
Implement Builder DP for HoaUser | Create Builder class and methods | Filip | 1h 30 mins | 1h 30mins |  |  | Methods done, needs tests and small changes
Receive noticeboard | Endpoint in Activity and Voting microservice | Filip | 30 mins(2-3h) | 15 mins |  | I was waiting for the skeleton of the activity and voting microservice and now that it is ready I have inspected it and have a plan | Edit one, after looking into everything for about an hour I see that it is going to take longer. Total around 5 hrs, as it takes time to understand and do everything
| Query the database | Filip | 30min(1h) | 0
| Test the new methods | Filip | 1h | 0
Notifications microservice testing | Writing tests | George | 2h 30 mins | 2h
As a user I want to be able to create activities | Resolve build and runtime errors | George | 30 mins | 30 mins
| Refactor activities create endpoint | George | 30 mins | 30 mins
| Wrapper Classes | Olek & Dimitar | 30 mins | 30 mins
| Structure Establishment | Olek & Dimitar | 1h | 1h
| Voting Strategies | Dimitar | 1h | 1h 30 mins
| Choices Methods and Testing Them | Dimitar | 1h | 1h 30 min
| Authentication | Dimitar | 2h | 2h 30 mins
| Authentication Testing | Dimitar | 1h 30 min | 1h
| Testing | Olek & Dimitar | 4h | 3h |  | Not everything is tested
| Repository Creation | Olek | 2h | 3h
The user must be able to join HOAs | Endpoint in HOA microservice | Atour | 2h | 3h
| Testing the new endpoint and methods | Atour | 1h 30m | 2h
The user must be able to leave a HOA | Endpoint in HOA microservice | Atour | 1h | 15m
| Testing the new endpoint and methods | Atour | 1h | 15m
The user must be able to vote for a board member of the HOA | Structure Establishment | Olek | 15 mins | 15 mins
User Story | Tasks | Assigned to | Estimated time | Actual time | Done? | Notes | Additional information
The user shall be able to see the notice board of the HOA they are part of | Create Hoa Endpoint & Verify the users identity | Filip | 2h | 3h |  | The reason it took longer was because I got lost when creating a commons module to avoid code duplication, but to no avail. Atour did it GJ to him!
| Forward request to Activity and Voting MS | Filip | 2h | 3h
| Test the methods | Filip | 1h 30 min | 2h
Creating a postman test suite | Creating a collection of requests to run | Filip | 1h | 1h
| Adding tests to them | Filip | 4h | 4h
Expanding postman tests | Making the tests run with gradle | Filip | 3h | 3h
The user should receive notifications once a proposal is accepted | Add endpoint to retrieve the emails of the users in the user microservice | Dimitar | 2h | 2h 30 m
Dimitar
| Test the endpoint | Dimitar | 1h | 45m
| Implement actual user service in the notifications microservice | Dimitar | 2h | 2h
Dimitar
| Make the user service communicate with the user microservice | Dimitar | 1h 30m | 2h 30m
Dimitar
| Test the methods in notifications | Dimitar | 2h | 2h
| Configure Rest Templates in A&E microservice | Dimitar | 30m | 15m
| Add event for ended proposal | Dimitar | 45m | 45m
| Implement communication with the hoa microservice to retrieve the ids of the members to send notifications | Dimitar | 1h | 1h 15m
Dimitar
Dimitar
| Implement communication with the notification microservice to send notifications | Dimitar | 45m | 30m
Dimitar
| Implement voting strategy for accepting proposals | Dimitar | 30m | 30m
| Test all of the above-mentioned methods | Dimitar | 4h | 5h
Fixes | Fix poor-quality tests from A&E microservice | Dimitar | 1h | 1h
Testing the HoaUserBuilder | Add a test suite | Filip | 2h | 2h
Testing for the Activity Microservice | Integration tests | Olek | 2h | 1h
The user should be able to see the history of their HOA | Readjust activity class to include timestamps | Olek | 30m | 2h
| Add endpoints for getting past and future activities | Olek | 2h | 1h 30m
| Readjust other methods and tests to incorporate changes to activities class and its children | Olek | 2h | 3h
| Refactor HOA module | Atour | 2h30 | 3h
| Add a commons module | Atour | 30m | 30m
| Make address and specificaddress embeddables | Atour | 30m | 30m
| Addresses should be able to handle non-integer values | Atour | 15m | 30m |  | Adjusting the old tests took a little longer than expected
| Leaving the HOA removes you as board member | Atour | 30m | 30m
| Member for at least 3 years | Atour | 15m | 15m
| Members cannot vote for themselves | Atour | 15m | 15m
| Members of the HOA can report eachother | Atour | 3h | 3h
| Only part of one board | Atour | 20m | 20m
| No more than 10yrs on one board | Atour | 20m | 20m
| Include activities-and-election in the pipeline | Atour | 15m | 15m
| Remove example-microservice | Atour | 5m | 5m
| User can apply for only one HOA board | Atour | 20m | 20m
Add director class to the UserBuilder | Add UserDirector class | Filip | 15m | 15m
| Add a test suite | Filip | 15m | 15m
The hoa must be able to host elections | Create application and Election process | George | 8h | 8h
| Host them upon the creation of a HOA | George | 3h | 3h
A user must be able to become a board member | Users must be able to apply for board members | George | 4h | 4h
| Users must be able to become board members | George | 3h | 3h
Voting for gatherings , elections, and proposals | Implementing voting for all of the Activity types | George | 8h | 8h
George
Boundary tests | Creating boundary tests for the models | Filip | 1h 30m | 1h 30m
| Add a testing suite to the activity module | Atour | 4h | 4h |  | Scaled back the expectation for 90% coverage because of unanticipated setbacks
| Refactor the activity module | Atour | 3h | 3h